## Project Timeline
Project Name:
Project Team Members:
Due Time: | Start of class | End of Day
Project Milestone | Due | Details | Notes from Standup with Instructor
Proposal + Team Contract | 2021-06-26 | Propose your idea to two (2) separate instructors for approval
Proof of Concept | 2021-06-29 | Can this idea turn into a reality? What do you need to do to prove it? The point is to identify any technical issues you may have. Determine if your project can be done.
Minimum Viable Product | 2021-07-01 | You have achieved the absolute minimum as far as necessary features show in PoC phase. This may look like you have solved your problem/challenge for at least one case.
Complete Project | 2021-07-10 | Iron out the kinks, receive feedback from peers and instructors, iterate over the MVP
First Draft Script and Demo | 2021-07-13 | Script must be complete and demo'd to instructors
Recording | 2021-07-15 | Zoom or Camtasia recording complete
Complete Presentation | 2021-07-15 | Any final touches / editing - Share with friends, family, and social media.
Present Project | Satuday 7/17 | Present Projects during graduation/friends & family

## Project Proposal
Project Name: | Team 2 - Investigate and Report - Ransomware
Project Team Members: | Rafael Encarnacion, Casey Mullins, Kim Young
Specifics For Your Project
Overview | The firm Encarnacion, Mullins and Young (EMY) is the target of a WannaCry attack. Our goal is to investigate the attack to determine what was exploited and how the attack could have been prevented or better contained and advise EMY on how to improve their cyber security posture.
PoC | Select a known WannaCry attack as our case study, use logs and post-mortems from actual attacks to recreate the scenario and work through the incident response and change management process to improve EMYs ability to stop sophisticated cyber attacks.
MVP
Complete Project | Lessons learned document/final incident report for general public, incident response techniques, tactics and procedures.
Stretch Goals | Create a training package for end users.

## External Resources
| Link | Notes:
Ex. Github |  | Ex. Repo for our code
Working Doc |  | ex. This is the doc we are sharing / brainstroming on